## Basic Data
Completion Schedule for Railway Project Bridges
Basic Data ¦ Sheet 1 ¦ As presented to the Minister (28-Sep-2026)
No. | Project Name | Sector | Phase / Stretch | Planned Completion Date | Revised Completion Date | Lengths Handed Over
1 | Construction of Railway Line (El-Manashi / 6th of October) Length: 67 km |  | Km 0 to Km 10 (10 km) | 30-Jun-2026 | 30-Nov-2026
|  |  | Km 10 to Km 31 (21 km) | 01-Mar-2027 | 30-Jun-2027 *
|  |  | Km 31 to Km 67 (36 km) | 30-Jun-2028 | 30-Jun-2028
2 | Line Doubling (Imbaba / El-Ittihad / El-Qabbari) From Beshtil to El-Ittihad – Length: 89 km |  | Km 4 to Km 25 (21 km) | 30-Aug-2026 | 30-Dec-2026 (handwritten)
|  |  | Km 25 to Km 52 (27 km) | 30-Jun-2026 | Handed over | 25 km handed over
|  |  | Km 52 to Km 93 (41 km) | 30-Mar-2027 | 30-Mar-2027 (handwritten) *
3 | Construction of Railway Line (El-Robeiky / Belbeis) Length: 57 km | Sector 1 | Completion of the L-shaped alignment from El-Robeiky to the Dry Port (Km 0 – Km 11) on the main line + Dry Port spur (12 km); total length 23 km | 30-Jun-2026 | 30-Oct-2026 | 3.5 km handed over; date being set to take over a further 4.5 km
|  | Sector 2 | Km 16 to Km 26 (10 km) | 30-Dec-2026 | 30-Mar-2027 *
|  | Sector 3 | Km 26 to Km 38 (12 km) | 30-Jun-2027 | 30-Jun-2027
|  | Sector 4 | Km 11 to Km 16 (5 km) | 30-Mar-2028 | 30-Jun-2028
Km 38 to Km 45 (7 km)
Notes: (*) Year on the scanned original is hand-corrected (printed 2026, overwritten to 2027). Read as 2027 since the printed 2026 revised date falls before the planned date. Confirm against the signed copy. Sector lengths reconcile with project totals: 10+21+36 = 67 km; 21+27+41 = 89 km; 23+10+12+5+7 = 57 km.